## Sheet1
|  | 2025 | [5 empty] | 2026
TASK | Task ID | July | August | September | October | November | December | January | February | March
TASK 1 | Purchasing -LED-Electronics-Connectors
TASK 2 | Desing Electronics (optical+ electronics+Programming)
TASK 3 | Desk Testing
TASK 4 | Redesing housing
TASK 5 | Camera testing adquisition Desktop experiments
TASK 6 | Shallow water Camera testing
TASK 7 | Deep water testing- Not funded yet-Seeking collaboration